## Slide 1
PRINCIPALES PRODUCTOS DEL PROYECTO | FECHA PLAN HITO
ID Project Charter: | 
Fecha Plan Inicio: 240508 | 
Fecha Plan Termino: 230608 | 
PROBLEMATICA/REQUERIMIENTOS)
S S S S S S S S S
Project Charter | 
Nombre del Proyecto: | Descripción:
ALCANCE PRELIMINAR DE PROYECTO
S S S S S
SUPUESTOS DEL PROYECTO | RESTRICCIONES
ANALISIS DE TRIPLE RESTRICCION | 
El tiempo de realización de proyecto se considera: | 
El costo de realización de proyecto se considera: | 
El alcance del proyecto se considera | 
GRUPO DE INTERES(PRELIMINAR) | ROL
Dirección General | Cliente
 | Sponsor
 | Project Manager
 | Team Process
 | XX
 | XXx
 | XXX
 | XXX
 | XXx
 | XXX
 | XXX
AAA
Prioridad 1
AA
Prioridad 2
A
Prioridad 3
Nombres/Firmas |  |  | 
Elaboró Project Manager | Autorizo Dir.de Proy. | Autorizo Sponsor | Autorizo Cliente
JUSTIFICACION/CASO DE NEGOCIO
S S S S S S S S S

## Slide 2: Project Charter
RESOURCES
Name Role % (Time)
Cesar Solórzano Project Champion 2%
Cesar Parra Project Champion 2%
Gustavo Ruiz Project Champion 2%
Roberto Saco Deployment Champion 2%
Juan C Pons Black Belt 100% Hortensia Molinar Master BB 5%
Enrique Hernández Finance Consultant 3%
Claudio Angulo BB Manager 5%
Marco Hernández Process Owner 3%
Alejandro Barco Green Belt Trained 10%
Jose Lenin Osorio Certified Green Belt 10%
Danae Astiz Certified Green Belt 10%
Alfonso Zárate Subject Matter Expert 10%
Luis López Subject Matter Expert 10%
Marco Aisawa Subject Matter Expert 30%
Román Saldaña Subject Matter Expert 25%
Title: Reduce Renewal Cards Returned Rate. Business: Operations México
PROBLEM STATEMENT
AMEX embosses approximately 336K Renewal cards annually which are sent by courier. From this total volume embossed and delivered to courier, 60% is delivered in Metropolitan Area and 40% Rest of the Country. From this 100%, 6.74% are returned to AMEX facilities for not being able to be delivered by courier at CM’s address to be reworked by the Delivery Services Area. (Yield = Fullfilment = 93.26%)
CUSTOMER IMPACT:
Customer Dissatisfaction Renewals: Occurs when CM does not receive the renewed card before the old one expires (At least 15 days before card expires).
RT TBASS (Non Received Average August, Feb – August, 2002) shows that
14.81 % have not received their card.
BUSINESS IMPACT:
Rework: Every card which is returned to AMEX facilities has to be reworked to find out if it is going to be Resent or Destroyed. U Cost = Cost charged by Courier for Returned card + Resent Cost (Analyzing). = $3.07 + $3.21
Cards Destroyed: U Cost = $0.82
Revenue Loss: Average Billing Spending Rate (Unit Cost percard a day= $26 USD)
COPQ= $17K Opex; $12KNonOpex // DPMO(LT)= 727K DPMO(ST) = 479K
SCOPE
This project will focus its efforts on reducing the number of Renewals cards that are produced in DC9000 , sent by courier and then returned to AMEX facilities.
Leverage Region Opportunities: Brazil, IDC and Argentina.
Leverage Process Opportunities: ECR’s.
MEASUREABLE GOAL
To decrease by may, 2003 50% the Return Rate of Renewals cards embossed by DC9000 and sent by courier to CM’s address.
SIGMA
Opportunity: Any Renewal card embossed in DC9000 and sent by courier to CM’s address.
Defect: Any Renewal card embossed in DC9000 and sent by courier to CM’s address that has been returned to AMEX facilities.
Data Type: Continuos.
Baseline (Jan – Sep, 2002) : ST Sigma = 0.05 (With Y Transformation to Continuos), LT Sigma =-0.60.
Data Source: - Production Files Jan – Sep, 2002 Extrapolated to a year.
- CPAS Plastics Jan – Sep, 2002 Average.
- Devolution Files D Services Jan- Sep, 2002.
FINANCIAL
Project Start Date: Oct 1st, 2002 Est. Completion: May 31st, 2002
Project Update: Dec 5st, 2002
Phase: Improve Apr-Dec Jan-Mar
2003 (9 Months) 2004 (3 Months)
Financial Impact
Rework Cost Reduction (Unit Cos= TBD) $ 15K $ 2K
Duplication Cost Reduction $ TBD $ TBD
Revenue Loss (Unit Cost = $26) $ 10K $ 2K
TOTAL Blue Box Benefits $ 25K $ 4K
Detail:
*Notes.-
Eliminating embossing costs, delivery costs and rework & duplacating costs due to analysis of returned cards.
In Revenue loss we are taking into consideration the Discount Rate to the Establishments = 2.5%